## The Risk Register
ID | Risk Category | Risk Description | Inherent Likelihood | Inherent Impact | Inherent Risk Level | Controls/Mitigation | Residual Likelihood | Residual Impact | Residual Risk Level | Risk Owner
R-001 | Cybersecurity | Hacker steals customer bank details from the website | 3 - Possible | 5 - Catastrophic | 15 - HIGH | • Install Firewalls • Implement (MFA) for all employees • Encrypt all data at rest and in transit | 2 - Unlikely | 5 - Catastrophic | 10 - MEDIUM | CISO
R-002 | Operations | A long power outage the office stops us from shipping the orders | 2 - Unlikely | 3 - Moderate | 6 - LOW | • Install UPS for essential systems • Backup generator for office • Cloud based system can work remotely •Mobile hotspot for critical work | 1 - Rare | 2 - Minor | 2 - LOW | Facilities Manager
R-003 | Human Error | An employee accidenTally deletes the entire customer database | 4 - Likely | 5 - Catastrophic | 20 - HIGH | • Apply RBAC permissions - not everyone needs delete permissions • "Soft delete" feature • Confirmation prompt for delete actions •Automated backups | 2 - Unlikely | 4 - Major | 8 - MEDIUM | IT Manager
R-004 | Compliance | New privacy law (like GDPR) if not followed may leading to fines | 3 - Possible | 5 - Catastrophic | 15 - HIGH | • Quarterly compliance review • Appoint a Data Protection Officer | 2 - Unlikely | 4 - Major | 8 - MEDIUM | Compliance Officer
R-005 | Vendor/Supply Chain | Our only supplier of a popular toy goes out of the business | 2 - Unlikely | 4 - Major | 8 - MEDIUM | • Keep at least 2 backup suppliers • Maintain Safety Stock | 1 - Rare | 3 - Moderate | 3 - LOW | Supply Chain Manager
R-006 | Cybersecurity | Ransomware attack locks all company files and systems | 3 - Possible | 5 - Catastrophic | 15 - HIGH | • Regular Automated backups stored offline • Phishing training for all employees • Quarterly incident response testing | 2 - Unlikely | 4 - Major | 8 - MEDIUM | CISO
R-007 | Technology/Infrastructure | Website goes down during peak shopping season (Black Friday) | 3 - Possible | 4 - Major | 12 - MEDIUM | • Load testing before peak seasons • Redundant hosting across multiple data centers • Use Cloud Services | 1 - Unlikely | 3 - Moderate | 3 - LOW | Web Developer Leader
R-008 | Physical Security | Unauthorized person gains access to office and steals equipment | 2 - Unlikely | 4 - Major | 8 - MEDIUM | • Card access system • Security Cameras at entrances • Visitor sign-in policy • Clean desk policy (no passwords on sticky notes) | 1 - Rare | 3 - Moderate | 3 - LOW | Facilities Manager

## Definations
RISK RATING DEFINITIONS
Likelihood Scale (How likely is it to happen)
Score | Level | Meaning
1 | Rare | Less the once every 5 year
2 | Unlikely | Once every 2-5 years
3 | Possible | About once per year
4 | Likely | Several times per year
5 | Almost Certain | Multiple times per months
Impact Scale (How bad would it be?)
Score | Level | Meaning
1 | Insignificant | <$1,000 loss, no customer impact
2 | Minor | $1K-$10K loss, few customer affected
3 | Moderate | $10K-$50K loss, some customer affected
4 | Major | $50K-$250K loss, many customer affected
5 | Catastrophic | >$250K loss, Business could fail
Risk Score (Likelihood * Impact)
Score | Level | Meaning
1--4 | LOW | Just Monitor
5--9 | MEDIUM | Watch closely, assign someone to check
10--14 | HIGH | Need plan ASAP
15--25 | CRITICAL | Fix NOW, immediately your boss immediately